## Slide 1: California Area Office Update
Beverly Miller, M.H.A., M.B.A.
July 19, 2017

## Slide 2: Desert Sage Youth Wellness Center – Now Open!

## Slide 3: Desert Sage Youth Wellness Center
State-of-the-art amenities (kitchen and classrooms)
Fully trained and motivated staff (38% Native)
Quiet and peaceful atmosphere
Individualized education program
24-hour on-site medical care
Gym, weight room, and recreational room
5 Family suites

## Slide 4: Desert Sage Youth Wellness Center
Forms and Applications are available here: https://www.ihs.gov/california/index.cfm/yrtc-project/yrtc-forms-apps/
For more information, please contact:
  Mark Espinosa
  Mark.Espinosa@ihs.gov
  951-708-4069 ext. 4039

## Slide 5: Sacred Oaks Healing Center Introduction
Request for Proposal of Selecting a Contractor
Yolo County Board of Supervisors Meeting
Project Timeline

## Slide 6: Request for Proposal (RFP) of Selecting a Contractor
Currently in Phase II (of II) of the RFP process
Estimated date to award contract – September 2017
Initial RFP required a cost-saving scope of work
  Bids coming in much higher than budget
    Cost increases in labor rates & current construction market (we are competing for contractors, not vice versa)

## Slide 7: Yolo County Board of Supervisors (BOS) Meeting
Held on June 27, 2017
Focused on:
  Project Timeline
  Drainage Study
  Emergency Services
  Broadband Connectivity
  Traffic Safety Study

## Slide 8: Yolo County Concerns: Traffic Improvements
Road Improvements Funding background:
  The IHS initial 2012 Traffic Study did not show the need for a left-hand turn lane
  Funding was appropriated by Congress in 2015 and did not include funding for County Road (CR) 31 improvements
  The subsequent 2017 study showed the need for a left-hand turn lane
    Associated with increased traffic on CR 31 between 2012 and 2017

## Slide 9: Yolo County Concerns: Traffic Improvements
Challenges:
  We are not authorized to complete work on a county road
  Congressional funding was not provided
    IHS legislation has provided Yolo County with multiple funding sources for our partnership to pursue
If the road safety improvements are not completed, their support the project is in question
The IHS is pursuing Tribal and County partnerships for a resolution
  As a Federal agency, the IHS is prohibited from pursuing these alternate funding sources

## Slide 10: In Summary
Emergency Response
  Evacuation procedures need to be addressed
  The IHS will address this during the operational phase of the project
Drainage/Flooding
  Initial thoughts are that our project will affect the surrounding area during a flood
  Flooding issues will be addressed during design/construction of the facility
Traffic Safety
  A left-hand turn lane is required for the safety of our patients and staff
  The funding for the left turn lane can be obtained through Tribal and County partnerships
Broadband Connectivity
  The IHS has the capability of connecting to fiber optic broadband service located along CR31

## Slide 11: Project Timeline
Request for Proposals (RFP) Issued: March 2017
2nd RFP Issued (due to overpriced proposals): June 2017
Estimated Date to Award Contract: September 2017
Estimated Date to Complete Design: April 2018
Estimated Date to Initiate Construction: June 2018
Estimated Construction Completion: August 2019

## Slide 12: Annual California Providers’ Continuing Medical Education
The IHS/CAO and CRIHB jointly hosted the Annual California Providers’ Continuing Medical Education event on May 22-24 in Sacramento
More than 350 providers, mid-level practitioners, and clinic support staff attended, earning over 1,000 IHS-sponsored CME credits/units towards clinic licensure
An array of topics offered

## Slide 13: Annual California Area Dental Continuing Education
The IHS/CAO and CRIHB jointly hosted the Annual California Area Dental Continuing Education event on May 15-18 in Sacramento
More than 400 dental staff (dentists, dental hygienists, and dental aides) attended the event and earned continuing dental education credits
An array of topics offered

## Slide 14: Thank You
Beverly Miller, M.H.A., M.B.A.
Beverly.Miller@ihs.gov
916-930-3981, ext. 312